## Summary
MedBridge Supply Co. — NIST CSF Gap Assessment Summary
Assessment Date: | June 2025
Assessed By: | Li Yopp, GRC Analyst
Framework: | NIST Cybersecurity Framework (CSF) 2.0
Company: | MedBridge Supply Co. (Fictional)
Priority Summary
Priority | Count | % of Total | Action Required
Critical | 4 | 14.81% | Immediate remediation — assign owner and start within 30 days
High | 9 | 33.33% | Remediate within 90 days — include in next sprint planning
Medium | 8 | 29.63% | Remediate within 180 days — track in risk register
Low | 6 | 22.22% | Remediate within 12 months — monitor and review quarterly
Function Maturity Overview
CSF Function | Subcategories Assessed | Avg Current Score | Avg Target Score | Avg Gap | Overall Maturity
GOVERN | 5 | 1.6 | 3.6 | 2 | Tier 1–2 (Partial → Risk Informed)
IDENTIFY | 6 | 1.7 | 3.3 | 1.7 | Tier 1–2 (Partial → Risk Informed)
PROTECT | 7 | 2.1 | 3.6 | 1.5 | Tier 2 (Risk Informed)
DETECT | 3 | 1.7 | 3.3 | 1.7 | Tier 1–2 (Partial → Risk Informed)
RESPOND | 3 | 1.3 | 3.3 | 2 | Tier 1 (Partial)
RECOVER | 3 | 1 | 3.3 | 2.3 | Tier 1 (Partial)

## Instructions
MedBridge Supply Co. — NIST CSF Gap Assessment
Framework: NIST Cybersecurity Framework (CSF) 2.0
Purpose | This assessment evaluates MedBridge Supply Co.'s current cybersecurity maturity against the NIST CSF 2.0 framework and identifies gaps relative to the target state.
Scoring Scale | 1 = Not implemented ¦ 2 = Partially implemented ¦ 3 = Largely implemented ¦ 4 = Fully implemented
How to use | Review each subcategory. Enter Current Score (1–4) and Target Score (1–4). Gap is calculated automatically. Add notes and owners for each finding.
Maturity Tiers | Tier 1 (Partial) ¦ Tier 2 (Risk Informed) ¦ Tier 3 (Repeatable) ¦ Tier 4 (Adaptive)
Assessment Date | June 2025
Assessed By | Li Yopp, GRC Analyst
Next Review | December 2025

## Gap Assessment
MedBridge Supply Co. — NIST CSF 2.0 Gap Assessment
Function | Category | Subcategory ID | Subcategory Description | Current Score (1–4) | Target Score (1–4) | Gap | Priority | Maturity Tier | Finding / Evidence | Recommended Action | Owner
GOVERN | Organizational Context | GV.OC-01 | Organizational mission and objectives are understood | 2 | 4 | 2 | High | Tier 2 | Mission documented informally; not linked to security strategy | Develop and publish security-aligned mission statement | CISO
GOVERN | Risk Management Strategy | GV.RM-01 | Risk management objectives are established and agreed upon | 1 | 4 | 3 | Critical | Tier 1 | No formal risk management strategy exists | Establish enterprise risk management policy and appetite statement | CISO / Board
GOVERN | Roles & Responsibilities | GV.RR-01 | Organizational leadership is responsible and accountable for cybersecurity risk | 2 | 4 | 2 | High | Tier 2 | Leadership awareness exists; accountability not formally assigned | Define RACI matrix for cybersecurity roles across departments | CISO / HR
GOVERN | Policy | GV.PO-01 | Policy for managing cybersecurity risks is established and communicated | 2 | 3 | 1 | Medium | Tier 2 | Acceptable use policy exists; not reviewed in 18 months | Review and update all security policies annually | GRC Analyst
GOVERN | Oversight | GV.OV-01 | Results of organization-wide cybersecurity risk management are reviewed by leadership | 1 | 3 | 2 | High | Tier 1 | No formal GRC reporting cadence to leadership | Establish quarterly risk reporting to executive team | GRC Analyst
IDENTIFY | Asset Management | ID.AM-01 | Inventories of hardware managed by the organization are maintained | 2 | 4 | 2 | High | Tier 2 | Partial asset inventory in spreadsheet; not automated | Implement asset management tool (e.g., Lansweeper or ServiceNow) | IT Manager
IDENTIFY | Asset Management | ID.AM-02 | Inventories of software managed by the organization are maintained | 2 | 3 | 1 | Medium | Tier 2 | Software list exists; shadow IT not tracked | Deploy software discovery scanning and review quarterly | IT Manager
IDENTIFY | Asset Management | ID.AM-05 | Assets are prioritized based on classification, criticality, and business value | 1 | 3 | 2 | High | Tier 1 | No formal data classification or asset criticality ranking | Develop data classification policy and asset criticality matrix | GRC Analyst / IT
IDENTIFY | Risk Assessment | ID.RA-01 | Vulnerabilities in assets are identified, validated, and recorded | 2 | 4 | 2 | High | Tier 2 | Vulnerability scans run ad hoc; no formal tracking | Implement monthly automated vulnerability scanning with remediation SLAs | IT Security
IDENTIFY | Risk Assessment | ID.RA-03 | Internal and external threats to the organization are identified and recorded | 2 | 3 | 1 | Medium | Tier 2 | Threat awareness informal; no documented threat library | Conduct annual threat modeling exercise; document findings in risk register | GRC Analyst
IDENTIFY | Improvement | ID.IM-01 | Improvements are identified from evaluations | 1 | 3 | 2 | High | Tier 1 | No post-incident or post-audit improvement tracking process | Implement lessons-learned process tied to risk register | GRC Analyst
PROTECT | Identity Management | PR.AA-01 | Identities and credentials for authorized users and services are managed | 3 | 4 | 1 | Medium | Tier 3 | MFA enforced for most systems; service accounts not reviewed | Extend MFA to all systems; implement quarterly access reviews | IT Security
PROTECT | Identity Management | PR.AA-03 | Users, services, and hardware are authenticated | 3 | 4 | 1 | Low | Tier 3 | SSO deployed; legacy applications use local auth | Migrate remaining legacy apps to SSO | IT Manager
PROTECT | Awareness & Training | PR.AT-01 | Personnel are provided awareness and training | 2 | 4 | 2 | High | Tier 2 | Annual security training; phishing simulations not conducted | Launch phishing simulation program (KnowBe4); quarterly campaigns | GRC Analyst
PROTECT | Data Security | PR.DS-01 | The confidentiality, integrity, and availability of data-at-rest are protected | 2 | 4 | 2 | High | Tier 2 | Encryption deployed on servers; endpoints inconsistent | Enforce full-disk encryption on all endpoints via MDM policy | IT Security
PROTECT | Data Security | PR.DS-02 | The confidentiality, integrity, and availability of data-in-transit are protected | 3 | 4 | 1 | Low | Tier 3 | TLS enforced on all external traffic; some internal services unencrypted | Enforce TLS on all internal service-to-service communication | Engineering
PROTECT | Platform Security | PR.PS-01 | Configuration management practices are established and applied | 1 | 3 | 2 | Critical | Tier 1 | No baseline security configurations (CIS Benchmarks) documented | Develop hardening standards aligned to CIS Benchmarks for all platforms | IT Security
PROTECT | Supply Chain | PR.SC-01 | Cybersecurity requirements are integrated into supplier and partner agreements | 1 | 4 | 3 | Critical | Tier 1 | No vendor security requirements in contracts | Develop vendor security addendum and integrate into procurement process | GRC Analyst / Legal
DETECT | Continuous Monitoring | DE.CM-01 | Networks and network services are monitored to find potentially adverse events | 2 | 4 | 2 | High | Tier 2 | Firewall logs reviewed manually; no SIEM in place | Evaluate and implement SIEM solution (e.g., Microsoft Sentinel) | IT Security
DETECT | Continuous Monitoring | DE.CM-03 | Personnel activity and technology usage are monitored to find potentially adverse events | 1 | 3 | 2 | High | Tier 1 | No user behavior monitoring or DLP controls | Implement DLP policies and user activity monitoring for sensitive data | IT Security
DETECT | Adverse Event Analysis | DE.AE-02 | Potentially adverse events are analyzed to better characterize the events | 2 | 3 | 1 | Medium | Tier 2 | Alert triage is manual; no documented runbooks | Develop alert triage runbooks and integrate with ticketing system | IT Security / GRC
RESPOND | Incident Management | RS.MA-01 | The incident response plan is executed in coordination with relevant third parties | 1 | 4 | 3 | Critical | Tier 1 | No formal incident response plan exists | Develop and test incident response plan aligned to NIST 800-61 | GRC Analyst / CISO
RESPOND | Incident Analysis | RS.AN-03 | Analysis is performed to establish what has taken place during an incident | 1 | 3 | 2 | High | Tier 1 | No forensic capability or documented analysis process | Establish incident analysis procedures and evidence preservation guidelines | IT Security
RESPOND | Incident Response Reporting | RS.CO-02 | Incidents are reported to appropriate authorities | 2 | 3 | 1 | Medium | Tier 2 | Informal notification process; regulatory reporting not documented | Document regulatory and contractual incident notification requirements | GRC Analyst / Legal
RECOVER | Incident Recovery Plan | RC.RP-01 | The recovery portion of the incident response plan is executed once initiated | 1 | 4 | 3 | Critical | Tier 1 | No documented recovery procedures; BCP/DR plan not established | Develop BCP and DR plan with defined RTO/RPO for critical systems | IT Manager / GRC
RECOVER | Incident Recovery Communication | RC.CO-03 | Recovery activities are communicated to internal and external stakeholders | 1 | 3 | 2 | High | Tier 1 | No stakeholder communication plan for recovery events | Develop crisis communication plan including client and regulatory notifications | GRC Analyst / Comms
RECOVER | Improvements | RC.IM-01 | Restoration activities are coordinated with internal and external parties | 1 | 3 | 2 | Medium | Tier 1 | No post-incident restoration coordination documented | Integrate recovery coordination steps into incident response plan | GRC Analyst