## POA&M Summary
POA&M Summary — MedBridge Supply Co.
System Name | MedBridge eProcurement SaaS Platform
System Owner | CISO / VP Engineering
Framework | NIST SP 800-171 Rev 2
POA&M Date | June 2025
Next Review | September 2025
Total Open Items | 9
In Progress | 3
Estimated Total Cost | $29,000–$20,000/yr

## POA&M
MedBridge Supply Co. — Plan of Action and Milestones (POA&M)
Aligned to NIST SP 800-171 Rev 2 ¦ System: MedBridge eProcurement SaaS Platform ¦ Classification: CUI-Adjacent
POA&M ID | NIST 800-171 Control | Control Description | Weakness / Deficiency | Resources Required | Scheduled Completion Date | Milestones | Milestone Status | Changes to Milestones | Responsible POC | Estimated Cost | POA&M Status
PM-001 | 3.1.1 | Limit system access to authorized users | No formal access review process; terminated employees may retain access | IT Manager (20 hrs), HR coordination | 2025-08-31 | M1: Document current access list (Jul 15) ¦ M2: Identify and remove stale accounts (Jul 31) ¦ M3: Implement quarterly review process (Aug 31) | M1: Complete ¦ M2: In Progress ¦ M3: Not Started | None | IT Manager | $0 (internal labor) | In Progress
PM-002 | 3.1.2 | Limit system access to types of transactions authorized users are permitted to execute | Role-based access control not fully implemented; some users have broader access than job function requires | IT Manager (30 hrs), application owners | 2025-09-30 | M1: Document role definitions (Aug 15) ¦ M2: Map users to roles (Sep 1) ¦ M3: Remediate over-provisioned accounts (Sep 30) | M1: Not Started ¦ M2: Not Started ¦ M3: Not Started | None | IT Manager / App Owners | $0 (internal labor) | Open
PM-003 | 3.3.1 | Create and retain system audit logs | Audit logging not enabled on all systems; log retention policy undefined | IT Security (25 hrs), potential SIEM licensing | 2025-10-31 | M1: Inventory systems requiring logging (Aug 1) ¦ M2: Enable logging on all critical systems (Sep 15) ¦ M3: Define and document retention policy (Oct 31) | M1: Not Started ¦ M2: Not Started ¦ M3: Not Started | SIEM evaluation in progress | IT Security | $8,000–$15,000/yr (SIEM) | Open
PM-004 | 3.4.1 | Establish baseline configurations for IT systems | No CIS Benchmark-aligned hardening standards defined; systems deployed with default configurations | IT Security (40 hrs), tooling for compliance scanning | 2025-10-31 | M1: Select applicable CIS Benchmarks (Aug 15) ¦ M2: Draft hardening standards (Sep 15) ¦ M3: Apply and validate on pilot systems (Oct 31) | M1: Not Started ¦ M2: Not Started ¦ M3: Not Started | None | IT Security | $0–$5,000 (tooling) | Open
PM-005 | 3.5.3 | Use multifactor authentication for local and network access | MFA not enforced on all systems; legacy applications use single-factor authentication | IT Manager (15 hrs), IdP configuration | 2025-08-31 | M1: Inventory non-MFA systems (Jul 31) ¦ M2: Enable MFA on critical systems (Aug 15) ¦ M3: Full MFA coverage or documented exceptions (Aug 31) | M1: Complete ¦ M2: In Progress ¦ M3: Not Started | Legacy app exceptions require architecture review | IT Manager | $0 (existing IdP) | In Progress
PM-006 | 3.6.1 | Establish operational incident handling capability | No documented incident response plan; no defined roles or procedures for security incidents | GRC Analyst (60 hrs), legal review | 2025-10-31 | M1: Draft IRP framework (Aug 31) ¦ M2: Legal and leadership review (Sep 30) ¦ M3: Tabletop exercise conducted (Oct 31) | M1: Not Started ¦ M2: Not Started ¦ M3: Not Started | None | GRC Analyst / CISO | $0 (internal labor) | Open
PM-007 | 3.11.1 | Periodically assess risk to organizational operations | No formal risk assessment process; risks identified ad hoc without documentation or tracking | GRC Analyst (40 hrs) | 2025-09-30 | M1: Develop risk assessment methodology (Aug 1) ¦ M2: Conduct initial enterprise risk assessment (Sep 1) ¦ M3: Publish risk register to leadership (Sep 30) | M1: In Progress ¦ M2: Not Started ¦ M3: Not Started | None | GRC Analyst | $0 (internal labor) | In Progress
PM-008 | 3.13.8 | Implement cryptographic mechanisms to prevent unauthorized disclosure during transmission | TLS not enforced on all internal service-to-service communication; some legacy APIs transmit data unencrypted | Engineering (20 hrs) | 2025-09-15 | M1: Inventory internal APIs and services (Aug 1) ¦ M2: Enable TLS on all internal traffic (Sep 15) | M1: Not Started ¦ M2: Not Started | None | Engineering Lead | $0 (configuration change) | Open
PM-009 | 3.14.1 | Identify, report, and correct system flaws | No formal vulnerability management program; patches applied ad hoc without tracking or SLAs | IT Security (30 hrs), vulnerability scanner licensing | 2025-08-31 | M1: Select and deploy vulnerability scanner (Jul 31) ¦ M2: Conduct baseline scan (Aug 15) ¦ M3: Define patching SLAs and remediation process (Aug 31) | M1: Complete ¦ M2: Not Started ¦ M3: Not Started | Scanner deployed (Tenable) | IT Security | $6,000/yr (scanner) | In Progress