## Risk Register
MedBridge Supply Co. — Information Security Risk Register
Risk ID | Risk Category | Risk Title | Risk Description | Threat Source | Likelihood (1–5) | Impact (1–5) | Inherent Risk Score | Risk Rating | Existing Controls | Residual Risk (Est.) | Recommended Treatment | Risk Owner | Target Remediation Date | Status
R-001 | Third-Party / Vendor | Unvetted vendor access to eProcurement platform | Third-party vendors onboarded without formal security review, creating risk of unauthorized access to client procurement data and PHI-adjacent records | External / Supply Chain | 4 | 5 | 20 | Critical | No formal vendor security questionnaire or access review process |  | Implement vendor risk questionnaire and tiered onboarding process; restrict vendor access to least-privilege | CISO / Procurement | 2025-09-30 | Open
R-002 | Access Control | Excessive privileged account access | Admin accounts not reviewed regularly; terminated employee accounts may retain access to critical systems | Internal / Operational | 3 | 5 | 15 | High | AD group management; offboarding checklist exists but not consistently followed |  | Implement quarterly access reviews; automate offboarding via HR-IT integration | IT Manager | 2025-08-31 | In Progress
R-003 | Data Security | Unencrypted sensitive data on endpoints | Employee laptops not consistently encrypted; loss or theft exposes procurement and client data | Internal / Physical | 3 | 4 | 12 | High | Server-side encryption deployed; endpoint policy inconsistent |  | Enforce full-disk encryption via MDM on all endpoints; verify compliance monthly | IT Security | 2025-07-31 | In Progress
R-004 | Incident Response | No formal incident response plan | Organization lacks documented IRP; response to data breach or ransomware would be uncoordinated and likely delayed | Internal / Operational | 4 | 5 | 20 | Critical | Ad hoc incident handling; escalation path informal |  | Develop IRP aligned to NIST 800-61; conduct tabletop exercise within 90 days of completion | GRC Analyst | 2025-10-31 | Open
R-005 | Business Continuity | No documented BCP or DR plan | Critical business functions and recovery procedures not documented; RTO/RPO not defined for eProcurement platform | Internal / Operational | 3 | 5 | 15 | High | Manual backup procedures exist; untested and undocumented |  | Develop BCP/DR plan; define RTO ≤ 4 hrs and RPO ≤ 24 hrs for critical systems; test annually | IT Manager / GRC | 2025-11-30 | Open
R-006 | Vulnerability Management | Unpatched systems in production | Inconsistent patch management process leaves systems exposed to known vulnerabilities; no formal SLA for critical patches | Internal / Technical | 4 | 4 | 16 | High | Patches applied manually on ad hoc basis; no tracking system |  | Implement automated patch management with SLAs: Critical ≤ 7 days, High ≤ 30 days | IT Security | 2025-08-31 | Open
R-007 | Security Awareness | Phishing susceptibility among staff | No phishing simulation program in place; staff awareness of social engineering tactics untested and likely inadequate | External / Human | 4 | 4 | 16 | High | Annual security awareness training completed by most staff; no simulations |  | Launch phishing simulation program (KnowBe4); target < 5% click rate within 6 months | GRC Analyst | 2025-09-30 | Open
R-008 | Configuration Management | Hardening standards not applied | No baseline security configurations defined for servers, endpoints, or cloud resources; systems may be deployed with insecure defaults | Internal / Technical | 3 | 4 | 12 | High | Some manual hardening applied; no documented standard or automated compliance check |  | Develop CIS Benchmark-aligned hardening standards; automate compliance scanning | IT Security | 2025-10-31 | Open
R-009 | Data Governance | Absence of data classification policy | Without a data classification policy, staff cannot identify sensitive data, leading to inconsistent handling, storage, and sharing of PHI-adjacent and financial data | Internal / Operational | 3 | 4 | 12 | High | Data types informally understood; no written policy or labeling system |  | Develop and publish data classification policy; train all staff within 60 days of publication | GRC Analyst / Legal | 2025-09-30 | Open
R-010 | Cloud Security | Misconfigured cloud storage buckets | Cloud storage (Azure Blob) not consistently configured with access controls; risk of inadvertent public exposure of client data | Internal / Technical | 3 | 5 | 15 | High | Azure storage accounts provisioned; access control review not performed |  | Conduct immediate cloud configuration review; implement Azure Policy for storage access enforcement | IT Security | 2025-07-15 | Open
R-011 | Regulatory Compliance | HIPAA breach notification gap | As a platform handling PHI-adjacent data, MedBridge may have breach notification obligations under HIPAA BAA terms; current process does not address 60-day notification requirement | External / Regulatory | 3 | 5 | 15 | High | BAAs in place with hospital clients; notification procedures not documented |  | Document breach notification procedures; define triggers, timelines, and responsible parties | GRC Analyst / Legal | 2025-09-30 | Open
R-012 | Physical Security | Visitor access controls insufficient | No formal visitor management process at Milwaukee HQ; visitors may access areas containing workstations with sensitive system access | Internal / Physical | 2 | 3 | 6 | Medium | Receptionist present during business hours; no sign-in log or escort policy |  | Implement visitor management policy; require escort for non-public areas; maintain sign-in log | Facilities / HR | 2025-10-31 | Open

## Scoring Guide
Risk Scoring Guide — MedBridge Supply Co.
Inherent Risk Score = Likelihood (1–5) × Impact (1–5)
Score Range | Risk Rating | Color | Response
20–25 | Critical | Red | Immediate action required — escalate to CISO and executive team within 24 hours
12–19 | High | Orange | Remediate within 90 days — assign owner and include in project planning
6–11 | Medium | Yellow | Remediate within 180 days — track in risk register and review monthly
1–5 | Low | Green | Accept or monitor — review annually or when environment changes